| ## HSC 2020 ## SBIRT - Screening, Brief Intervention, and Referral to Treatment ## Mental Health & Substance Abuse [MHSA] Community Health Committee ## Minutes |  |  |  |
| --- | --- | --- | --- |
| DATE: | Wednesday, May 17, 2017 | LOCATION: | HHS 413 |
| PRESIDING: | Shelby Kuhn; Kari Keller |  |  |
| PRESENT: | Amanda Anhalt (LCHC), Jessica Miner (MHA), Sara Sandman (Plymouth HS), Connie Frank (RCS), Stacie Kuck (Parent/volunteer), Bryce DeRoos (Oostburg School District), Jenny Vorpagel (Public Health), Libby Holte (Public Health), Shelby Kuhn (Aurora), Kari Keller (Public Health), Mary Paluchniak (St. Nicks) |  |  |
| ABSENT/EXCUSED: | Ann Bachrach |  |  |
| RECORDER: | Jenny Vorpagel |  |  |
| NEXT MEETING: | June 21st, 2017 8:05am-9am Health and Human Services Building Room 372 |  |  |

| ITEM | DISCUSSION/CONCLUSION/RECOMMENDATIONS |
| --- | --- |
| Welcome and Introductions |  |
| Report Out on Action Steps from Previous Meeting | - Food for August trainings: Mary and Ann—Preliminary work has been done, they will be meeting again soon. - April School district meeting: Kari went over the “Practice Based Evidence” handout. Another meeting with the schools has not been set. Elkhart Lake, Random Lake, Plymouth, Oostburg, Cedar Grove, Sheboygan Falls schools are participating. - Coordinate “community provider” summit: Cindy (see next section) - School Board convo: Kristin - MHA partnership: Kristin - Aurora commitment: Shelby |
| Follow-up - SBIRT in the Schools - SBIRT in Healthcare settings | - School/SBIRT Initiative - Kristin Stearns has been working with schools to develop partnership and support around the “severe” 5% who may or may not be appropriate for SBIRT services (keep it separate!) - Cindy is working to coordinate a provider summit- Kristin is asking MHA to help invite; Shelby and Kristin likely to facilitate; will set up school-provider meeting down the road after August training - Cindy is working on creating a Referral to Treatment group. Also working on an MOU that the people involved will work with the referrals that are given from the schools. Looking to set a meeting in June. - Sheboygan schools may be backing out of SBIRT- Kristin to intervene. Right now we don’t know if SASD is participating. Stacie said she would look into it. - Schools needed to complete implementation plans by 5/15/17. Kari will look into whether they have all been submitted. - Discussion took place if enough people will be attending the August trainings and whether we can consolidate to one training instead of two, which would save $3,000. If SASD does not participate, there should only be one training. Decision to be made by June 1st. - Some discussion in progress re: confidentiality and referrals in the works. Schools and State/WISH will work through in training. - Dr. Murthy talked with new manager of Plymouth Family Practice about SBIRT and received a positive response. They will be meeting with her re: a pilot project in a healthcare setting. - No update on Prevea SBIRT |
| Change Maker Grant/UW Madison Wisconsin Partnership Program | - Medical College of Wisconsin Changemaker grant - http://www.med.wisc.edu/wisconsin-partnership-program/community-opportunity-grants-program - UW-Madison grant is being redesigned; new framework to be announced May 2017 |
| Report Out for Full Committee - Summary - Barriers - Celebrations - Asks | Roundtable— - Kari and one other person from Public Health will be attending QPR (Question, Persuade, Refer) training in June. 20-30 people will be trained to train others in the community. The Stigma committee is putting together the training. All day training on June 16th. |
| Don’t forget these items as part of action plan: Education/Prevention Access to Service Coordination/Continuity of Care Health Literacy | Review the CHIP goals and objectives We are on the last year of the CHIP, and the new CHIP is being worked on now. The leadership council will look at the data and decide what to include in the next CHIP. They would like to keep going a lot of the efforts that are currently going on, including SBIRT. |
| Action Steps and Person Responsible | Shelby will contact Tracy Lee-Johnson for Aurora and get in touch with Kristin By June first the decision will be made to have either one or two school trainings. |