| ## HSC 2020 ## SBIRT - Screening, Brief Intervention, and Referral to Treatment ## SCHOOL Subcommitte ## Agenda |  |  |  |
| --- | --- | --- | --- |
| DATE: | 01/27/2017 1:00-2:00 PM | LOCATION: | Department of Health and Human Services, Room 413 |
| PRESIDING: | Shelby Kuhn(Aurora); Kari Keller(DPH) |  |  |
| PRESENT: | Ann Buechel Haack (ELG), Char Pachniak (Horizon4 Girls), Byrce De Roos (OSD), Tamra O’Keefe (CGB), Cindy VanderWeele (DPH), Libby Holte (DPH), Sara Sandman, (PLY), Vicky Schneider (DPH), Amanda Anhalt(LCHC), Tom Malmstad(RL), Regan Haulotte SASD), Ann Roy (SHEB FALLS) |  |  |
| ABSENT/EXCUSED: | HG |  |  |
| RECORDER: | Cindy VanderWeele |  |  |
| NEXT MEETING: | 02/15/2017 8:00-10:00 AM at Department of Health and Human Services, Room 372 |  |  |

| ITEM | DISCUSSION/CONCLUSION/RECOMMENDATIONS |
| --- | --- |
| HSC 2020 Leadership Meeting Report (01/23/2017) | Kari shared Kristin’s report from the meeting as follows: · All schools are on board with SBIRT training moving forward except Kohler. Schools are working on implementation project plan given by Scott. o LCHC will give a list of referral organizations for section 8a of form with the help of MHA. Will send to Tom by 2/6. - Kristin reviewed the SBIRT process again, explained MI/BI and how this can be done in a group also. - Two major concerns: School Counselors have struggled to find resources, connect with resources in the community for those students already needing MH/AODA support. Counselors are not confident in the outside system. Examples were no follow through on referral agency part, difficulty getting returned calls, sometimes never getting a returned call, etc. - Solutions Discussed: · Creating a system of coordinated care (point person(s) within each outside referral system. · Understanding all potential referral sources including: provider type, scope, insurances taken, sliding fee, eligibility, etc. · Potential for Warm Handoffs from schools/family to outside referral/family - Items for HSC2020: · Set up a meeting with major referral parties to discuss supporting the following solutions. · Working with MHA on educating counselors on potential resources School Counselors and staff time being taking by the 5-10% of students that have extreme behavioral and emotional Issues. Children coming out of Lincoln Hills, Winnebago, etc. and coming to attend the schools with no plan. Staff feel they have very little support from Law Enforcement, the Medical Community, and HHS. - Solutions Discussed: · Tom and a couple of school staff are creating a flow chart of each type of child needing help and resources to be used. 1st Track: SBIRT; 2nd Track: Path/Referral to Services; 3rd Track: Extreme Behavior Issues. · HSC2020 that we take a leadership role in convening a group to look further into support the schools and families with kids who have extreme behavioral issues. It was discussed with Tom Eggebrecht to have HHS staff work as a backup to school staff for SBIRT, this is not feasible, nor are Aurora or Prevea able to work in that capacity. |
| Agenda for 02/15/2017 SBIRT School Meeting | Schools are asked to bring their Implementation Plan even if it is a draft to the meeting. |
| Headcount for August SBIRT School Trainings | Initial numbers of expected attendees to the training are: ELG-6 OSD-5 RL-6 CGB-5 SASD-18,12 SF-8 Ply-12 HG- 5 Kiel would like to participate if there is space available. It was suggested that schools identify any interventionists. Amanda Anhalt w LCHC will also be trained. Possibly 2 MHA staff as well. |
| Completion of the School SBIRT Training and Implementation Project Plan | Schools represented discussed that they would like to follow the plan that Tom has developed for their school plans. Tom will share with the schools and will send a draft to Scott at DPI prior to the 2/15 meeting. |