| ## HSC 2020 ## SBIRT - Screening, Brief Intervention, and Referral to Treatment ## Mental Health & Substance Abuse [MHSA] Community Health Committee ## Minutes |  |  |  |
| --- | --- | --- | --- |
| DATE: | Wednesday, December 21st 8:05-9:00am | LOCATION: | Department of Health and Human Services, Room 372 |
| PRESIDING: | Shelby Kuhn; Kari Keller |  |  |
| PRESENT: | Jenny Vorpagel, Libby Holte, Cindy Vander Weele, Vicky Schneider, Trisha Erpelding, Dharmesh Murthy, Connie Frank, Amanda Anhalt, Shelby Kuhn, Kari Keller |  |  |
| ABSENT/EXCUSED: | Regan Haulotte, Sara Sandman, Mary Paluchniak |  |  |
| RECORDER: | Jenny Vorpagel |  |  |
| NEXT MEETING: | Wednesday, January 18th, 8:05am-9:00am |  |  |

| ITEM | DISCUSSION/CONCLUSION/RECOMMENDATIONS |
| --- | --- |
| Welcome and Introductions |  |
| Report Out on Action Steps from Previous Meeting | Lutheran and Christian High- Tom Malmstadt contacted the schools. Kari reported that Christian is interested and Lutheran has not responded. Dean Becker-Shelby contacted him. Talked about getting together has healthcare agencies. UW Madison Grant- Shelby-Specifically targeted to communities working on CHIPs. They decided to change the grant and will let us know when they have finalized the process. |
| Follow-up - Clinic/Hospital Implementation - SBIRT in Healthcare - SBIRT and the Schools | - Review progress of School/SBIRT initiative: ways that HSC2020 can help this effort succeed - Upcoming meetings-1/6—superintendents meeting at Oostburg school district office in the high school-8am. The speaker at that meeting would like everyone attending to read these FAQ sheet. There will be a training 8/2-3 and 8/8-9. One training will be filled by schools; they are hoping the other one could be community/health care partners. There is follow-up work after the trainings. 1/27 meeting with school personnel, they will be meeting regularly. - Barriers and solutions—Concerns are people are thinking they will be expected to do more with less. It was suggested that everyone gets together twice a year to discuss best practice. Discussion took place about where schools would be sending referrals. Libby suggested we create our own FAQ sheet. http://dpi.wi.gov/sites/default/files/imce/sspw/pdf/gainssmanual.pdf - Discussion took place on what the “Acuity” money is that is being used to pay for trainings. A letter is needed from Captain Veeser to allocate the money to us. - Group discussed possibility of retired counselors helping out. Do they still have their licenses? - Area healthcare involvement/future planning - Review of status with Healthcare/SBIRT initiative - Aurora/Prevea efforts- status-Shelby in contact with Tracy Lee-Johnson-no new updates. - Barriers and solutions |
| Change Maker Grant/UW Madison Wisconsin Partnership Program | - Medical College of Wisconsin Changemaker grant - http://www.med.wisc.edu/wisconsin-partnership-program/community-opportunity-grants-program/44947 - Timelines for 2017? Deadlines will be early in the year- February? |
| Report Out for Full Committee - Summary - Barriers - Celebrations - Asks |  |
| Don’t forget these items as part of action plan: Education/Prevention Access to Service Coordination/Continuity of Care Health Literacy | Review the CHIP goals and objectives |
| Other- Brief round table and updates on organizations/community events. LCHC new addition to open soon! |  |